## List sheet name of project
2 |  |  | Project Online Food Ordering System
| term |  | Quản lý dự án phần mền
| Group |  | TMPS
| Description |  | null
| No | Sheet Name | Link Name | Description
| 1 | WBS | WBS | Xây dụng sơ đồ WBS.
| 2 | Gantt Chart | Gantt Chart | Cập nhập nhiêm vụ của dự án lên sơ đồ Gantt chart.
| 3 | Resources ($) task. | Resources ($) task. | Tính tiền các nhiệm vụ
| 4 | Communiation Plan | Communiation Plan | Lịch trình cụ thể
| 5 | RACI | RACI | Xây dụng ma trận RACI
| 6 | Budget | Budget | Tính chi phí cho dự án.

## WBS
Online Food Ordering System WBS Spreadsheet
Milestone | ID | Task | Owner | Duration (days) | Notes | Back
Requirement | 1.1 | Cost Analyst | Financial Analyst | 5 | Financial analysis for the project
| 1.2 | Collect information | Information collection specialist | 3 | Collect requests from customers
| 1.3 | Information analysis and processing | Information Analyst | 5 | Analyze customer requirements
Design | 2.1 | Module design | Design Specialist | 7 | Design modules for the project
| 2.2 | Stream controller design | Design Specialist | 7 | Design relationships between tables or modules
| 2.3 | UI Design | Design Specialist | 5 | Design the interface for the website
| 2.4 | Database Design | Design Specialist | 4 | Database design
Execution and Installation | 3.1 | Building Front-end | Specialist Developer Front-end | 15 | Build interfaces according to blueprints
| 3.2 | Buiding Database | Specialist Developer Database | 3 | Build a place to store the website's databuild a place to store the website's data
| 3.3 | Buiding Back-end | Specialist Developer Back-end | 10 | Build server to blueprints
System integration and testing | 4.1 | Integrate subpages | Specialist Developer Front-end | 5 | Integrate subsites after construction is complete
| 4.2 | Sort subpages | Specialist Developer Front-end | 3 | Arrange subpages after construction is complete
| 4.3 | Testing website | The Quality Assurance Tester | 5 | Test the subsites after the build is complete
Operation and maintenance | 5.1 | Bug fixes and maintenance | Developer | 7 | Correct errors during operation
| 5.2 | Update and upgrade as required | Developer | 5 | Upgrade and update the requirements of the desired custome

## Gantt Chart
Task | Description | Time start (day) | Time work (day) | Back
O | Cost Analyst | 0 | 5
A | Collect information | 5 | 3
B | Information analysis and processing | 8 | 5
C | Module design | 13 | 7
D | Stream controller design | 20 | 7
E | UI Design | 20 | 5
F | Database Design | 20 | 4
G | Buiding Front-end | 27 | 15
H | Buiding Database | 24 | 5
I | Buiding Back-end | 29 | 10
J | Integrate subpages | 42 | 5
K | Sort subpages | 47 | 3
L | Testing website | 42 | 5
M | Bug fixes and maintenance | 50 | 7
N | Update and upgrade as required | 57 | 5

## Resources ($) task.
Owner | Task | Time start (day) | Time work (day) | Quantitative Costs | Back
Financial Analyst | Cost Analyst | 0 | 5 | 500
Information collection specialist | Collect information | 5 | 3 | 500
Information Analyst | Information analysis and processing | 8 | 5 | 500
Design Specialist | Module design | 13 | 7 | 600
Design Specialist | Stream controller design | 20 | 7 | 550
Design Specialist | UI Design | 20 | 5 | 600
Design Specialist | Database Design | 20 | 4 | 500
Specialist Developer Front-end | Buiding Front-end | 27 | 15 | 800
Specialist Developer Database | Buiding Database | 24 | 5 | 800
Specialist Developer Back-end | Buiding Back-end | 29 | 10 | 950
Specialist Developer Front-end | Integrate subpages | 42 | 5 | 600
Specialist Developer Front-end | Sort subpages | 47 | 3 | 500
The Quality Assurance Tester | Testing website | 42 | 5 | 500
Developer | Bug fixes and maintenance | 50 | 7 | 600
Developer | Update and upgrade as required | 57 | 5 | 500

## Communiation Plan
Task | Owner | Description | Time start (day) | Time work (day) | Back
O | Financial Analyst | Cost Analyst | 0 | 5
A | Information collection specialist | Collect information | 5 | 3
B | Information Analyst | Information analysis and processing | 8 | 5
C | Design Specialist | Module design | 13 | 7
D | Design Specialist | Stream controller design | 20 | 7
E | Design Specialist | UI Design | 20 | 5
F | Design Specialist | Database Design | 20 | 4
G | Specialist Developer Front-end | Buiding Front-end | 27 | 15
H | Specialist Developer Database | Buiding Database | 24 | 5
I | Specialist Developer Back-end | Buiding Back-end | 29 | 10
J | Specialist Developer Front-end | Integrate subpages | 42 | 5
K | Specialist Developer Front-end | Sort subpages | 47 | 3
L | The Quality Assurance Tester | Testing website | 42 | 5
M | Developer | Bug fixes and maintenance | 50 | 7
N | Developer | Update and upgrade as required | 57 | 5

## RACI
| Project Tasks | Product Manager | UI Designer | Content Writer | Financial Analyst | Tester | VP of Product | VP of Design | CTO | CEO | Design Director | Back
| Collect information |  |  | R |  |  | A |  |  | I
| Information analysis and processing |  |  | R |  |  | A | I | I | I
| Cost Analysis |  |  |  | R |  | A | I | I | C
| Module design |  | R |  |  |  | A |  |  | I
| Stream controller design |  | R |  |  |  |  | C |  | I | A
| UI Design |  | R |  |  |  |  | C | I | I | A
| Database Design |  | R |  |  |  |  | C | I | I | A
| Buiding Front-end | R |  |  |  | A |  |  | I | I
| Buiding Database | R |  |  |  | A |  |  | I | I
| Buiding Back-end | R |  |  |  | A |  |  | I | I
| Integrate subpages | R |  |  |  |  | A |  | I | I
| Sort subpages | R | [5 empty] | A |  | I
| Testing website |  |  |  |  | R | A |  |  | I
| Bug fixes and maintenance | R |  |  |  |  | A |  |  | I
| Update and upgrade as required | R |  |  |  |  | A |  |  | I
Responsible
Accountable
Consulted
Informed
| Product Manager | UI Designer | Content Writer | Financial Analyst | Tester | VP of Product | VP of Design | CTO | CEO | Design Director
Owner23 | Nguyễn Văn Đông Nguyễn Công Đạt | Nguyễn Văn Hào | Nguyễn Quang Phú | Nguyễn Phú Lâm | Lê Thị Anh Thư | Hồ Anh Tài | Nguyễn Văn Thoại | Võ Thị Lệ Công | Hoàn văn Kiệt | Nguyễn Gia Lâm

## Budget
|  |  |  | Labor |  |  |  | Fixed |  |  |  | BALANCE
|  |  | Planned Hours | Actual Hours | $/HR | Travel | Equipment |  | Misc. | BUDGETED | ACTUAL | UNDER/OVER | Back
WBS | Project Tasks | Assigned To: | [7 empty] | 9000 | 8000 | 1000
1.1 | Cost Analyst | Nguyen Van Dong | 8 | 8 | 50 |  |  |  |  | 500 | 400 | 100
1.2 | Collect information | Nguyen Quang Phu | 8 | 8 | 50 | 50 |  |  |  | 500 | 450 | 50
1.3 | Information analysis and processing | Nguyen Quang Phu | 8 | 8 | 50 | 90 |  |  |  | 500 | 490 | 10
2.1 | Module design | Nguyen Van Hao | 8 | 8 | 55 |  |  |  | 25 | 600 | 465 | 135
2.2 | Stream controller design | Nguyen Van Hao | 8 | 8 | 55 |  |  |  |  | 550 | 440 | 110
2.3 | UI Design | Nguyen Cong Dat | 8 | 8 | 60 |  |  |  | 35 | 600 | 515 | 85
2.4 | Database Design | Nguyen Quang Phu | 8 | 8 | 50 |  |  |  |  | 500 | 400 | 100
3.1 | Building Front-end | Nguyen Cong Dat | 8 | 8 | 60 |  | 300 |  |  | 800 | 780 | 20
3.2 | Buiding Database | Nguyen Van Hao | 8 | 8 | 55 |  | 300 |  |  | 800 | 740 | 60
3.3 | Buiding Back-end | Nguyen Van Dong | 8 | 8 | 65 |  | 300 |  | 25 | 950 | 845 | 105
4.1 | Integrate subpages | Nguyen Cong Dat | 8 | 8 | 60 |  |  |  |  | 600 | 480 | 120
4.2 | Sort subpages | Nguyen Cong Dat | 8 | 8 | 60 |  |  |  |  | 500 | 480 | 20
4.3 | Testing website | Nguyen Van Hao | 8 | 8 | 55 |  |  |  | 15 | 500 | 455 | 45
5.1 | Bug fixes and maintenance | Nguyen Van Dong | 8 | 8 | 60 |  |  | 100 |  | 600 | 580 | 20
5.2 | Update and upgrade as required | Nguyen Van Dong | 8 | 8 | 60 |  |  |  |  | 500 | 480 | 20
| SUBTOTAL |  |  |  | 6760 | 140 | 900 | 100 | 100 | 9000 | 8000 | 1000